## 📋 Overview
MI-BCI Research WBS — Predicting Motor Imagery Performance from Resting-State EEG
Predicting MI-BCI Performance from Resting-State EEG using ML Baseline → GCN ¦ PhysioNet Schalk et al. ¦ 109 subjects ¦ 64 ch ¦ 160 Hz ¦ Supervisor: Dr. Harish Kumar NG ¦ VIT Chennai — Centre for Neuroinformatics
PURPOSE | This workbook is the complete PMP-style execution roadmap for predicting MI-BCI performance from resting-state EEG — from project kick-off to top-tier journal acceptance. Every task, subtask, milestone, acceptance criterion, and deadline is documented so that no step is missed that could cause rejection or major revision.
STRUCTURE | Sheet 1 (this sheet): overview and legend. Sheet 2: EMBC 2026 track — 4-page conference paper, ~16 weeks. Sheet 3: Top-Tier Journal track — full study, ~12 months (JNE / IEEE TNSRE / NeuroImage). Sheet 4: Quality Gates — pre-submission checklists; pass every gate before submitting. Sheet 5: Gantt — visual timeline for both tracks.
HOW TO USE | Update the STATUS column weekly. Turn subtasks GREEN when done, AMBER when in progress, RED when blocked. Never submit to a venue until all Quality Gate checks for that track are ticked ✅. Milestone rows (gold) are hard gates — do not proceed until supervisor sign-off.
STATUS LEGEND
✅ Done | Task fully completed and verified
🔄 In Progress | Task actively being worked on
⬜ Not Started | Not yet begun
🚫 Blocked | Blocked — needs action before proceeding
🏁 Milestone | Key deliverable gate — do not skip
TRACK SUMMARY
Track | Target Venue | Duration | Phases | Sheet
EMBC 2026 | IEEE EMBC 2026 Conference (4-page paper) | ~16 weeks | 6 phases | 📄 EMBC Track
Journal Full Study | JNE / TNSRE / NeuroImage (full paper) | ~12 months | 8 phases | 📰 Journal Track

## 📄 EMBC Track
EMBC 2026 — Conference Paper Track (4-Page IEEE Paper)
Target: IEEE Engineering in Medicine and Biology Conference 2026 ¦ Submission window: ~Jan–Feb 2026 ¦ Total duration: 16 weeks
ID | Phase / Task | Subtask / Deliverable | Acceptance Criteria | Owner | Duration | Week | Status
PHASE 1: DATA & ENVIRONMENT SETUP
1.1 | Environment Setup | Install Python 3.10+, CUDA, PyTorch, PyG, MNE-Python, Braindecode | pip install completes; import torch_geometric succeeds | Student | 3 days | 1 | ⬜ Not Started
1.1a |  | Download PhysioNet dataset via MNE: mne.datasets.eegbci.load_data() for all 109 subjects | Data folder present; 109 subjects confirmed; no corrupt EDF files | Student | 1 day | 1 | ⬜ Not Started
1.1b |  | Verify: 64 channels, 160 Hz, 10-10 system; map run numbers (Runs 1-2=rest; 4-6,8-10,12-14=MI) | CSV summary of channel count and run mapping; no degenerate subjects | Student | 1 day | 1 | ⬜ Not Started
1.1c |  | Set up GitHub repo: README, .gitignore, requirements.txt, folder structure (data/preprocessing/models/results/) | Repo public; supervisor added as collaborator; CI passes | Student | 1 day | 1 | ⬜ Not Started
1.2 | Feasibility Pilot | Run PLV estimation on 2 subjects in alpha + beta bands to confirm stability | PLV matrices plotted; alpha PLV variance across epochs < 0.15 | Student | 2 days | 2 | ⬜ Not Started
1.2a |  | Test epoch lengths: 2 s vs 4 s for resting state; select optimal for PLV reliability | Epoch length decision documented with justification in lab notebook | Student | 1 day | 2 | ⬜ Not Started
1.2b |  | Test sparsification thresholds: top 10%, 15%, 20% PLV/wPLI edges retained | Best threshold recorded; sensitivity table saved as CSV | Student | 1 day | 2 | ⬜ Not Started
M1 | 🏁 🏁 MILESTONE 1 | Environment verified, PhysioNet loaded, PLV feasibility confirmed | All 1.x subtasks ✅; pilot PLV matrices reviewed and approved by supervisor | Supervisor sign-off | — | 2 | 🏁 Milestone
PHASE 2: PREPROCESSING PIPELINE
2.1 | EEG Preprocessing | Implement full preprocessing pipeline in MNE-Python for resting-state runs (1-2) | Pipeline script runs end-to-end on all 109 subjects without error | Student | 4 days | 3 | ⬜ Not Started
2.1a |  | Apply notch filter at 60 Hz (US dataset); zero-phase FIR bandpass 1-40 Hz; document filter order | PSD plots confirm 60 Hz suppression; filter parameters in config.yaml | Student | 1 day | 3 | ⬜ Not Started
2.1b |  | Downsample to 128 Hz using raw.resample(128, npad='auto') after anti-aliasing filter | New sampling rate confirmed; Nyquist = 64 Hz covers full analysis range | Student | 0.5 day | 3 | ⬜ Not Started
2.1c |  | Run extended Infomax ICA; apply ICLabel for automatic IC rejection; log ICs removed per subject | Mean ± SD of ICs removed documented; no subject loses >50% signal variance | Student | 2 days | 3 | ⬜ Not Started
2.1d |  | Re-reference to average reference; segment resting state into 2-s non-overlapping epochs | Shape check: (n_epochs, 64, n_times) per subject; no negative epoch counts | Student | 1 day | 4 | ⬜ Not Started
2.1e |  | Automated epoch rejection: ±100 µV threshold; log rejection rate per subject; flag if >30% rejected | Rejection rate CSV saved; minimum 30 clean epochs per subject confirmed | Student | 0.5 day | 4 | ⬜ Not Started
2.2 | Feature Extraction — ML Input | Compute hand-crafted EEG features for Stage 1 ML models (flat feature vector per subject) | Feature matrix shape: 109 subjects × N features; saved as .csv + .npy | Student | 4 days | 4-5 | ⬜ Not Started
2.2a |  | Band power per electrode per band: delta(1-4), theta(4-8), alpha(8-12), beta(13-30), gamma(30-40) Hz → 5×64=320 features | Power values in µV²/Hz; z-score normalised across subjects | Student | 1 day | 4 | ⬜ Not Started
2.2b |  | PLV and wPLI between all 64×64 electrode pairs in alpha and beta bands; flatten upper triangle: 2016 features per band | Connectivity matrices plotted for 3 subjects; wPLI included for volume conduction robustness | Student | 2 days | 5 | ⬜ Not Started
2.2c |  | Entropy features: Sample Entropy (m=2, r=0.2×SD) and Hjorth parameters per electrode | Feature vector per subject confirmed; no NaN or Inf values | Student | 1 day | 5 | ⬜ Not Started
2.3 | Graph Construction — GCN Input | Build PyTorch Geometric Data objects: (x, edge_index, edge_attr, y) per subject | DataLoader iterates without error; 109 graph objects saved | Student | 2 days | 5-6 | ⬜ Not Started
2.3a |  | Nodes=64 electrodes; node features X=[64×5] band power; edges=thresholded PLV/wPLI adjacency A=[64×64] | Graph objects inspect correctly: x.shape=(64,5), edge_index valid | Student | 1 day | 5 | ⬜ Not Started
2.3b |  | Apply best sparsification threshold from 1.2b; compute mean node degree; visualise 3 good vs 3 poor performer graphs | Structural difference visible; mean degree logged per band | Student | 1 day | 6 | ⬜ Not Started
M2 | 🏁 🏁 MILESTONE 2 | Preprocessing complete; feature matrix and graph dataset built for all 109 subjects | All 2.x subtasks ✅; dataset statistics table generated; supervisor reviewed | Supervisor sign-off | — | 6 | 🏁 Milestone
PHASE 3: MI LABELLING & BASELINE MODELS
3.1 | MI Task Performance Labelling | Train within-subject MI decoder (CSP+LDA or EEGNet) on MI task runs (4-6, 8-10, 12-14) using 5-fold CV | Per-subject MI accuracy recorded; histogram of 109 accuracies generated | Student | 3 days | 6-7 | ⬜ Not Started
3.1a |  | Define good/poor performer threshold explicitly (e.g., median split or 70%); check class balance | Threshold documented with justification; class distribution: good n=X, poor n=Y | Student | 1 day | 7 | ⬜ Not Started
3.1b |  | Prepare both binary labels (classification) and continuous accuracy (regression) label files | Two label files saved: labels_binary.csv and labels_continuous.csv | Student | 0.5 day | 7 | ⬜ Not Started
3.2 | Stage 1: ML Baseline Models | Train RF, XGBoost, SVM, Ridge Regression on hand-crafted features under LOSO-CV (leave-one-subject-out) | All 4 models trained; LOSO fold indices saved for reuse in Stage 2 | Student | 5 days | 7-8 | ⬜ Not Started
3.2a |  | Random Forest: tune n_estimators(100-500), max_depth; XGBoost: tune lr, max_depth, subsample via grid search | Best hyperparameters per model logged; no data leakage across LOSO folds | Student | 2 days | 7 | ⬜ Not Started
3.2b |  | SVM (RBF kernel): tune C and gamma via inner CV; Ridge Regression: tune alpha regularisation | Hyperparameter search results saved; SVM trained on z-score normalised features | Student | 1 day | 8 | ⬜ Not Started
3.2c |  | Report per-model: Balanced Accuracy, AUC-ROC, F1, mean±SD across 109 LOSO folds | Results table (Table 1 draft): 4 ML models × 3 metrics; no selective reporting | Student | 1 day | 8 | ⬜ Not Started
3.2d |  | Run permutation test (n=1000 label shuffles) for each ML model; report p-value | All models statistically above chance (p<0.05); permutation null distributions plotted | Student | 1 day | 8 | ⬜ Not Started
M3 | 🏁 🏁 MILESTONE 3 | MI labels frozen; Stage 1 ML baseline results in hand | Label files frozen; ML comparison table produced; supervisor reviewed | Supervisor sign-off | — | 8 | 🏁 Milestone
PHASE 4: GCN MODEL & COMPARISON
4.1 | GCN Architecture Implementation | Implement 2-layer GCN: GCNConv(5→64)→ReLU→Dropout(0.5)→GCNConv(64→32)→ReLU→GlobalMeanPool→Linear→output | Forward pass runs without error; parameter count logged; gradients confirmed | Student | 4 days | 9-10 | ⬜ Not Started
4.1a |  | Add batch normalisation between GCN layers; implement early stopping (patience=20, monitor val loss) | Loss curves saved per fold; no NaN losses; best checkpoint saved | Student | 1 day | 9 | ⬜ Not Started
4.1b |  | Use EXACT same 109 LOSO fold indices as Stage 1 (load from saved file) — non-negotiable for fair comparison | Fold index file loaded and verified; identical train/test splits confirmed | Student | 0.5 day | 9 | ⬜ Not Started
4.2 | GCN Training and Evaluation | Train GCN on 109 LOSO folds; report same metrics as ML baseline (Balanced Accuracy, AUC-ROC, F1) | GCN row added to Table 1; per-fold results CSV saved | Student | 3 days | 10 | ⬜ Not Started
4.2a |  | Run McNemar's test (classification) or Wilcoxon test (regression): GCN vs best ML model | Statistical test p-value reported; effect size computed | Student | 1 day | 10 | ⬜ Not Started
4.2b |  | Ablation: run GCN with fully-connected graph (no threshold) vs thresholded — does topology matter? | Ablation result reported; topology contribution quantified | Student | 1 day | 10 | ⬜ Not Started
4.3 | Feature Importance & Interpretability | RF/XGBoost feature importances as EEG scalp topomaps; GNNExplainer edge importance maps | Topomap figure shows sensorimotor electrode dominance; edge importance aligns with connectivity | Student | 3 days | 11 | ⬜ Not Started
4.3a |  | Compare ML feature importance and GCN edge importance — do both point to same electrodes? | Agreement or disagreement documented; neuroscience interpretation written (3 paragraphs) | Student | 1 day | 11 | ⬜ Not Started
M4 | 🏁 🏁 MILESTONE 4 | Stage 1 vs Stage 2 comparison complete; interpretability figures ready | All models in Table 1; stats test done; topomap figures at 300 dpi; supervisor reviewed | Supervisor sign-off | — | 11 | 🏁 Milestone
PHASE 5: PAPER WRITING (IEEE 4-PAGE FORMAT)
5.1 | Outline & Section Allocation | Agree section structure and page budget with supervisor before writing | 1-page outline approved by supervisor; figure list agreed | Student+Supervisor | 1 day | 12 | ⬜ Not Started
5.2 | Introduction (≤0.4 pages) | State BCI prediction problem, gap in literature (resting→MI), two-stage ML+GCN contribution | Reviewer identifies gap and contribution in 60 seconds; 2 clear contributions listed | Student | 1 day | 12 | ⬜ Not Started
5.3 | Methods (≤1.2 pages) | Dataset, preprocessing, feature extraction, ML models, GCN architecture, LOSO evaluation | Fully reproducible; another lab can implement from this section alone | Student | 3 days | 12-13 | ⬜ Not Started
5.3a |  | Draw pipeline architecture figure: Resting EEG → Preprocessing → Features → ML+GCN → MI Prediction | Figure legible at column width; all stages labelled; 300 dpi | Student | 1 day | 12 | ⬜ Not Started
5.4 | Results (≤1.0 pages) | Table 1 (all 5 models), feature importance topomap, GCN edge importance figure | All figures fit in 4 pages; no result stated without a statistic | Student | 2 days | 13 | ⬜ Not Started
5.5 | Discussion & Conclusion (≤0.4 pages) | Neurophysiological interpretation; which resting features predict MI?; honest limitations | Limitations present; no overclaim of accuracy; framed as proof-of-concept | Student | 1 day | 13 | ⬜ Not Started
5.6 | References (IEEE format) | ≥15 references; all cited in text; no broken DOIs; IEEE citation style | Reference list formatted; all DOIs verified | Student | 1 day | 13 | ⬜ Not Started
5.7 | Internal Review & Revision | Full paper reviewed by supervisor; all tracked changes applied | Supervisor approval saved; tracked changes resolved; Quality Gates sheet fully ticked | Supervisor | 3 days | 14 | ⬜ Not Started
M5 | 🏁 🏁 MILESTONE 5 | Paper draft approved by supervisor | Supervisor signs off; paper passes all Quality Gate checks (Sheet 4) | Supervisor sign-off | — | 14 | 🏁 Milestone
PHASE 6: SUBMISSION & POST-SUBMISSION
6.1 | arXiv Preprint | Upload to arXiv (eess.SP or cs.LG) before EMBC submission | arXiv paper ID obtained; URL sent to supervisor | Student | 1 day | 15 | ⬜ Not Started
6.2 | IEEE ConfTool Submission | Create account, fill metadata, upload PDF + figures; IEEE PDF checker passes | Confirmation email received; submission ID saved; zero PDF checker errors | Student | 1 day | 15 | ⬜ Not Started
6.3 | Code Release | GitHub repo public: README, requirements.txt, run script; fresh env reproduces Table 1 in <1 hour | Supervisor confirms code runs; repo URL in paper | Student | 1 day | 15 | ⬜ Not Started
6.4 | Rebuttal Preparation (if reviews received) | Categorise all reviewer comments: major/minor/reject argument; write point-by-point rebuttal | Each reviewer comment addressed; no new results introduced in rebuttal | Student+Supervisor | 3 days | 16 | ⬜ Not Started
M6 | 🏁 🏁 MILESTONE 6 — EMBC SUBMITTED | Paper submitted to EMBC 2026 | Submission ID confirmed; arXiv preprint live; code repo public | Supervisor sign-off | — | 15 | 🏁 Milestone

## 📰 Journal Track
Top-Tier Journal Track — Full Study (JNE / IEEE TNSRE / NeuroImage)
Builds on EMBC paper — adds wPLI robustness, extended ablations, full interpretability analysis, and journal-standard manuscript ¦ Duration: ~12 months
ID | Phase / Task | Subtask / Deliverable | Acceptance Criteria | Owner | Duration | Month | Status
PHASE J1: FOUNDATION (Months 1–2) — Shared with EMBC Track
J1.1 | Complete EMBC Phases 1–4 | All preprocessing, MI labelling, ML baseline, GCN model from EMBC track | EMBC track Milestones M1–M4 all ✅ | Student | 8 weeks | 1–2 | ⬜ Not Started
J1.2 |  | Extend ML ablations: PLV vs wPLI vs coherence as connectivity metric; report all in extended ablation table | 3-metric comparison table with 95% CIs; best config selected and justified | Student | 1 week | 2 | ⬜ Not Started
J1.3 |  | Extend GCN ablations: 2-layer vs 3-layer GCN; GCN vs GAT; global mean vs attention pooling | Extended ablation table (3×3); best GCN configuration locked | Student | 1 week | 2 | ⬜ Not Started
MJ1 | 🏁 🏁 MILESTONE J1 | Foundation complete — EMBC results reproduced and extended | All EMBC milestones ✅; extended ablation table approved | Supervisor sign-off | — | 2 | 🏁 Milestone
PHASE J2: ROBUSTNESS ANALYSES (Month 3)
J2.1 | wPLI Robustness Analysis | Repeat entire Stage 1 and Stage 2 pipeline using wPLI instead of PLV as connectivity metric | All ML and GCN models retrained on wPLI features; conclusions confirmed stable or discrepancy explained | Student | 1 week | 3 | ⬜ Not Started
J2.2 |  | Test eyes-open vs eyes-closed resting runs separately — which predicts MI accuracy better? | Comparison table: EO vs EC prediction performance across all models | Student | 3 days | 3 | ⬜ Not Started
J2.3 |  | Test resting window length sensitivity: 1 min vs 2 min vs 3 min of resting-state data | Performance trend across window lengths; clinical deployability implication documented | Student | 3 days | 3 | ⬜ Not Started
J2.4 |  | Test MI label threshold sensitivity: 60%, 70%, 80% accuracy cutoffs — are model rankings stable? | Rankings consistent across all thresholds; or instability documented and discussed | Student | 2 days | 3 | ⬜ Not Started
J2.5 |  | Test GCN edge threshold sensitivity: 10%, 15%, 20% edge density — do conclusions hold? | Performance reported for each threshold; optimal threshold confirmed | Student | 2 days | 3 | ⬜ Not Started
J2.6 |  | Demographic confounds: extract age/sex from PhysioNet metadata; test correlation with MI accuracy | Linear regression results reported; covariates added to models if significant | Student | 2 days | 3 | ⬜ Not Started
MJ2 | 🏁 🏁 MILESTONE J2 | Robustness analyses complete — conclusions confirmed stable | All sensitivity tables generated; wPLI results consistent; supervisor reviewed | Supervisor sign-off | — | 3 | 🏁 Milestone
PHASE J3: EXTENDED INTERPRETABILITY (Month 4)
J3.1 | Deep Feature Importance Analysis | RF/XGBoost feature importances: plot top-30 features as ranked bar chart and EEG scalp topomaps | Topomaps show sensorimotor electrode dominance; alpha/beta bands confirmed as key predictors | Student | 2 days | 4 | ⬜ Not Started
J3.2 |  | Ridge Regression coefficient analysis: map positive vs negative predictors to electrode/band space | Coefficient map shows spatial specificity; comparison with RF/XGBoost features documented | Student | 1 day | 4 | ⬜ Not Started
J3.3 | GCN Edge Importance Analysis | Apply GNNExplainer (PyG built-in) per subject per LOSO fold; extract per-edge importance scores | Edge importance scores saved per fold; averaged across good vs poor performer groups | Student | 3 days | 4 | ⬜ Not Started
J3.4 |  | Visualise edge importance as connectivity topomaps: which electrode pairs are most informative? | Topomap figures for good performers, poor performers, and difference at 300 dpi | Student | 2 days | 4 | ⬜ Not Started
J3.5 |  | Ablation: remove top 10% most important edges — measure GCN accuracy drop (causal validation) | Accuracy drop quantified; confirms attended edges are causally important, not spurious | Student | 2 days | 4 | ⬜ Not Started
J3.6 |  | Neurophysiological interpretation: do important features align with mu rhythm / sensorimotor literature? | 3-paragraph interpretation written; supervisor approves narrative before manuscript draft | Student | 2 days | 4 | ⬜ Not Started
MJ3 | 🏁 🏁 MILESTONE J3 | Interpretability analysis publication-ready | All figures at 300 dpi; edge ablation complete; neuroscience narrative approved | Supervisor sign-off | — | 4 | 🏁 Milestone
PHASE J4: FULL MANUSCRIPT WRITING (Months 5–8)
J4.1 | Venue Selection & Author Agreement | Decide: JNE vs IEEE TNSRE vs NeuroImage; agree author order; download submission guidelines | Submission portal account created; author list finalised; guidelines saved | Supervisor | 1 day | 5 | ⬜ Not Started
J4.2 | Introduction (≤0.6 pages) | BCI performance prediction gap; resting-state → MI rationale; two-stage contribution; 3 bulleted contributions | Reviewer identifies gap within 90 seconds; 3 contributions clearly stated | Student | 2 days | 5 | ⬜ Not Started
J4.3 | Related Work (≤1 page) | Cover: EEG BCI performance prediction, GNN for EEG, resting-state BCI predictors, ML vs DL comparison | All existing BCI prediction papers cited; gap clearly positioned vs prior work | Student | 3 days | 5 | ⬜ Not Started
J4.4 | Methods (≤2 pages) | Dataset, preprocessing, MI labelling, feature extraction, ML models, GCN architecture, LOSO, statistical tests | Fully reproducible; no ambiguity; another lab can re-implement from this section | Student | 5 days | 6 | ⬜ Not Started
J4.4a |  | Include formal pipeline figure (vector graphic): Resting EEG → Preprocessing → Features → ML+GCN → Prediction | Figure readable at single-column and double-column widths; all components labelled | Student | 2 days | 6 | ⬜ Not Started
J4.5 | Results (≤2 pages) | Table 1 (all 5 models), ablation table (wPLI/PLV/coherence), interpretability figures, sensitivity analysis | All figures at 300 dpi; every number has CI or p-value; no selective reporting | Student | 4 days | 7 | ⬜ Not Started
J4.6 | Discussion (≤1 page) | Para 1: does GCN beat ML? what does graph topology add? Para 2: neurophysiological interpretation Para 3: wPLI volume conduction Para 4: clinical framing Para 5: limitations Para 6: future work | Limitations honest; clinical claims framed as proof-of-concept only; no overclaiming | Student | 2 days | 7 | ⬜ Not Started
J4.7 | Conclusion (≤0.3 pages) | 3–5 sentences; no new information; contributions match Introduction | Conclusion mirrors contributions listed in Introduction exactly | Student | 0.5 day | 7 | ⬜ Not Started
J4.8 | References | ≥35 references; all DOIs verified; journal citation style (IEEE or APA per venue) | Zero broken links; all cited papers appear in text; format matches journal style | Student | 1 day | 7 | ⬜ Not Started
J4.9 | Supplementary Material | Code, extended ablation tables, per-subject accuracy breakdown, all sensitivity analysis results | Supplement ≤15 pages; all claims in main paper verifiable from supplement | Student | 2 days | 8 | ⬜ Not Started
MJ4 | 🏁 🏁 MILESTONE J4 | Full draft complete | All sections written; supervisor first read complete; Quality Gates sheet reviewed | Supervisor sign-off | — | 8 | 🏁 Milestone
PHASE J5: INTERNAL REVIEW CYCLE (Month 9)
J5.1 | Supervisor Full Review (Round 1) | Supervisor reads and comments on complete draft | Tracked-changes document returned within 10 days | Supervisor | 10 days | 9 | ⬜ Not Started
J5.2 |  | Student applies all tracked changes; writes response-to-supervisor letter (mirrors rebuttal format) | Response letter written; all comments addressed or disputed with justification | Student | 5 days | 9 | ⬜ Not Started
J5.3 | Language & Style Check | Grammarly / native-speaker proofread; passive voice <25%; no ambiguous sentences | Zero grammatical errors; readability score documented | Student | 2 days | 9 | ⬜ Not Started
J5.4 | Quality Gate Checklist | Work through every item in Sheet 4 — Quality Gates; no RED items remain | All boxes ticked; supervisor final written approval obtained | Student+Supervisor | 1 day | 9 | ⬜ Not Started
MJ5 | 🏁 🏁 MILESTONE J5 | Paper passes all Quality Gates | Quality Gate sheet fully ticked; supervisor final approval in writing | Supervisor sign-off | — | 9 | 🏁 Milestone
PHASE J6: PRE-SUBMISSION PREPARATION (Month 10)
J6.1 | arXiv Preprint | Upload final version to arXiv (eess.SP or q-bio.NC); announce on ResearchGate / LinkedIn | arXiv ID obtained; supervisor co-authors listed; URL shared | Student | 1 day | 10 | ⬜ Not Started
J6.2 | Code Repository Release | GitHub repo: clean code, README, requirements.txt (pinned versions), sample run notebook | Fresh conda env reproduces Table 1 result in <1 hour; supervisor confirms | Student | 2 days | 10 | ⬜ Not Started
J6.3 | Cover Letter | Write cover letter: scope fit, novelty, no dual submission, ethics statement (PhysioNet = public dataset) | Supervisor approves letter; no dual submission clause confirmed | Student+Supervisor | 1 day | 10 | ⬜ Not Started
J6.4 | Journal Submission Portal | Create account, fill metadata, upload all files, check formatting; confirm page/figure/supplement size limits | Submission confirmation email received; manuscript ID saved; PDF renders correctly | Student | 1 day | 10 | ⬜ Not Started
MJ6 | 🏁 🏁 MILESTONE J6 — JOURNAL SUBMITTED | Paper submitted to target journal | Manuscript ID confirmed; all files accepted by portal; arXiv live; code public | Supervisor sign-off | — | 10 | 🏁 Milestone
PHASE J7: REVIEW RESPONSE (Months 11–12, if applicable)
J7.1 | Reviewer Response Strategy | Categorise all reviewer comments: major / minor / reject argument; agree strategy with supervisor | Comment classification table created; strategy documented | Supervisor | 2 days | 11 | ⬜ Not Started
J7.2 | Write Point-by-Point Rebuttal | Address every comment; run new experiments if reviewer requests within 2 weeks | Every comment has a numbered response; new data clearly marked; no evasive answers | Student | 7 days | 11 | ⬜ Not Started
J7.3 | Revised Manuscript | Highlight all changes in revision PDF (track changes or colour-coded); update supplement | Revision letter + revised manuscript uploaded to portal; all reviewer concerns addressed | Student+Supervisor | 3 days | 12 | ⬜ Not Started
MJ7 | 🏁 🏁 MILESTONE J7 | Revision submitted | Revision confirmation email received; all reviewer comments addressed | Supervisor sign-off | — | 12 | 🏁 Milestone

## ✅ Quality Gates
Quality Gates — Pre-Submission Checklists
Every item must be ✅ before submission. A single RED item = do not submit. These are exactly what peer reviewers check.
✓ | Category | Specific Check | EMBC Required | Journal Required | Notes
DATA & REPRODUCIBILITY
☐ | DATA | PhysioNet dataset publicly available and cited: Schalk et al. (2004) | ✅ Required | ✅ Required | Cite dataset in Methods
☐ | DATA | All 109 subjects processed; per-subject epoch count logged after preprocessing | ✅ Required | ✅ Required | Report mean ± SD epoch count
☐ | DATA | Exclusion criteria pre-registered before analysis; excluded subjects logged with reason | ✅ Required | ✅ Required | Prevents post-hoc bias
☐ | DATA | Preprocessing parameters fully specified: filter cutoffs, ICA method, epoch length, rejection threshold | ✅ Required | ✅ Required | config.yaml in GitHub repo
☐ | DATA | Downsample to 128 Hz documented; 60 Hz notch filter applied (US dataset) | ✅ Required | ✅ Required | PhysioNet = US 60 Hz line noise
☐ | DATA | Code released on GitHub before submission; README enables 1-hour reproduction | ✅ Required | ✅ Required | Link in paper Methods
☐ | DATA | wPLI computed alongside PLV — volume conduction confound addressed | ✅ Required | ✅ Required | Critical reviewer concern
METHODOLOGY
☐ | METHOD | LOSO cross-validation used for ALL models with IDENTICAL fold indices | ✅ Required | ✅ Required | Fold indices saved to file
☐ | METHOD | MI labels generated by validated within-subject decoder (CSP+LDA or EEGNet) | ✅ Required | ✅ Required | Label generation method cited
☐ | METHOD | Good/poor performer threshold defined before model training; class balance reported | ✅ Required | ✅ Required | Median split or justified cutoff
☐ | METHOD | All 4 ML baselines (RF, XGBoost, SVM, Ridge) included and reported | ✅ Required | ✅ Required | No cherry-picking models
☐ | METHOD | GCN uses exact same LOSO folds as ML baseline — verified by loading fold file | ✅ Required | ✅ Required | Mandatory for fair comparison
☐ | METHOD | Graph topology ablation: thresholded vs fully-connected GCN comparison | ✅ Required | ✅ Required | Tests value of graph structure
☐ | METHOD | Sensitivity analyses: wPLI vs PLV, window length, label threshold, edge density | ⬜ Optional | ✅ Required | Robustness is journal standard
STATISTICS
☐ | STATS | Balanced Accuracy used as primary metric (handles class imbalance) | ✅ Required | ✅ Required | Not raw accuracy
☐ | STATS | 95% confidence intervals reported for all LOSO accuracy values | ✅ Required | ✅ Required | Mean ± SD across 109 folds
☐ | STATS | Permutation test (n=1000) for every model — p-value confirms above-chance | ✅ Required | ✅ Required | Mandatory statistical validation
☐ | STATS | McNemar's or Wilcoxon test: GCN vs best ML model — p-value and effect size | ✅ Required | ✅ Required | Claimed improvement must be tested
☐ | STATS | All models in same results table; identical metrics; no selective reporting | ✅ Required | ✅ Required | Reviewers look for cherry-picking
☐ | STATS | Effect size (Cohen's d or r) computed for main comparison | ⬜ Optional | ✅ Required | Journal standard for significance
INTERPRETABILITY
☐ | INTERP | RF/XGBoost feature importances plotted as EEG scalp topomaps | ✅ Required | ✅ Required | Neurophysiological interpretation
☐ | INTERP | GNNExplainer edge importance maps computed and visualised | ✅ Required | ✅ Required | Confirms edges causally important
☐ | INTERP | Ablation: top-10% edges removed — GCN accuracy drop quantified | ✅ Required | ✅ Required | Causal validation of interpretability
☐ | INTERP | ML important features and GCN edge importance compared — do they agree? | ⬜ Optional | ✅ Required | Cross-validates biological validity
☐ | INTERP | Neuroscience interpretation: relates findings to mu rhythm / sensorimotor literature | ✅ Required | ✅ Required | Required for neuroscience journals
☐ | INTERP | All figures at ≥300 dpi; readable at column width | ✅ Required | ✅ Required | Check BEFORE submission
WRITING & FRAMING
☐ | WRITE | Pipeline figure: all stages labelled; legible at column width; 300 dpi | ✅ Required | ✅ Required | Reviewers scan figures first
☐ | WRITE | Clinical claims framed as proof-of-concept — NOT deployment-ready tool | ✅ Required | ✅ Required | Overclaiming = rejection
☐ | WRITE | Limitations section present and honest: 160 Hz, healthy subjects, single dataset | ✅ Required | ✅ Required | Credibility requires honesty
☐ | WRITE | Introduction: gap and contributions identifiable in 90 seconds | ✅ Required | ✅ Required | Standard reviewer test
☐ | WRITE | All references have verified DOIs; ≥15 for EMBC; ≥35 for journal | ✅ ≥15 | ✅ ≥35 | No broken links
☐ | WRITE | Language proofread; no grammatical errors; passive voice <25% | ✅ Required | ✅ Required | Run Grammarly minimum
☐ | WRITE | No dual submission to other archival venue | ✅ Required | ✅ Required | Automatic rejection if violated
ETHICS & COMPLIANCE
☐ | ETHICS | IRB/ethics statement in Methods — note PhysioNet is a public dataset (no IRB needed) | ✅ Required | ✅ Required | State 'publicly available dataset'
☐ | ETHICS | Author contributions statement prepared (CRediT taxonomy for journals) | ✅ Required | ✅ Required | Required by most journals
☐ | ETHICS | Acknowledgements includes VIT Chennai CNI + funding source if applicable | ✅ Required | ✅ Required | Supervisor to confirm
☐ | ETHICS | PDF passes venue format checker (IEEE PDF Xplore / journal portal) | ✅ Required | ✅ Required | Check 48h before deadline
☐ | ETHICS | Cover letter written: scope fit, novelty, no dual submission, data ethics | ⬜ Not required | ✅ Required | Journal-only requirement
☐ | ETHICS | arXiv preprint uploaded before submission | ✅ Required | ✅ Required | Establishes priority
☐ | ETHICS | Supervisor has given explicit written approval to submit | ✅ Required | ✅ Required | Email confirmation saved

## 📅 Gantt
Project Gantt Chart — EMBC Track (Weeks) & Journal Track (Months)
EMBC 2026 Track — 16 Weeks
ID | Phase / Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
P1 | Data & Environment Setup
M1 | 🏁 Milestone 1 | bar: W2
P2 | Preprocessing & Feature Extraction
M2 | 🏁 Milestone 2 | bar: W6
P3 | MI Labelling & ML Baseline
M3 | 🏁 Milestone 3 | bar: W8
P4 | GCN Model & Comparison
M4 | 🏁 Milestone 4 | bar: W11
P5 | Paper Writing
M5 | 🏁 Milestone 5 (Draft OK) | bar: W14
P6 | Submission & Post-Submission
M6 | 🏁 EMBC SUBMITTED | bar: W15
Top-Tier Journal Track — 12 Months
ID | Phase | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
J1 | Foundation (EMBC phases 1–4)
MJ1 | 🏁 Milestone J1 | bar: W2; W13 to W16
J2 | Robustness Analyses
MJ2 | 🏁 Milestone J2 | bar: W3; W13 to W16
J3 | Extended Interpretability
MJ3 | 🏁 Milestone J3 | bar: W4; W13 to W16
J4 | Full Manuscript Writing
MJ4 | 🏁 Milestone J4 (Draft) | bar: W8; W13 to W16
J5 | Internal Review Cycle
MJ5 | 🏁 Quality Gates Passed | bar: W9; W13 to W16
J6 | Pre-Submission Preparation
MJ6 | 🏁 JOURNAL SUBMITTED | bar: W10; W13 to W16
J7 | Review Response (if needed)
MJ7 | 🏁 Revision Submitted | bar: W12 to W16
LEGEND
| EMBC Phase | W2: Journal Phase; W4: Milestone ▲; W6: Submission; W8: Review Response